## Sheet1
Project : EnergyLink Network
Task which are Initially not in Requirement
S No. | This are the new psds and we done with the functionality and layout, and it is not in use | Time(In Hours)
1
1.1 | EL_business_directory_payment_v14 (1.1) | 6 hour
This psd for upgrade listing in business directory
1.2 | EL_business_directory_upgradelisting_v14(1.2) | 4 hour
Upgrade listing form basic to 200 or 300 , 200 to 300
1.3 | EL_business_Subcategories_v14_abc(1.3) | 7 hour
business directory category page link on ENERGYLINK tab
1.4 | EL_jobs_a-l_list_v14(1.4) | 5 hour
Energy Job page
1.5 | EL_business_jobspage_admin_v14(1.5) | 5 hour
Energy Job page
1.6 | EL_business_listing_v14(1.6) | 5 hour
Business directory page
1.7 | EL_business_profile_completion_v14(1.7) | 8 hour
profile page
| TOTAL | 40 hour
S No. | Did Changes in psd layout and functionality | Time(In Hours)
2
2.1 | EL_business_Drilldown_p1_v13(2.1) | 10 hour
This is 200 listing form , we change it totally(as your Recruitment )
2.2 | EL_business_listing300_v14(2.2) | 14 hour
This is 300 listing form , we change it totally(as your Recruitment )
2.3 | EL_business_upgrade_Listing200_v14(2.3) | 8 hour
Upgrade listing form 200 to 300.(change functionality)
2.4 | EL_business_rego_v14(2.4) | 7 hour
This is basic listing form , we change it totally(as your Recruitment )
| TOTAL | 39 hour
S No. | User profile page changes | Time(In Hours)
3 | We Done this task with three resources
3 | We done with the profile page changes
3.1 | wireframe for profile page. | 4 hour
3.2 | EnergyLink profile page is done as like Client requirement. Here user view or edit there profile as like ( Linkedin) user profile.We add fields as client require. | 20 hour
3.3 | User activity page:- in that page all member, friend, groups activity are showing .and a tab for my activity which show current user acitivity. | 15hour
3.4 | We changed energy Event page as like site other page as like (buddpress pages) | 8 hour
3.5 | We change energy group page as like other pages(buddypress).Here admin update there group or other users are view ,join and comment that group .here admin invite or remove member form group. | 18 hour
3.6 | We changes with my company tab as like other pages. | 6 hour
3.7 | We totally changed buddypress theme for that changes. | 14 hour
| TOTAL | 85 hour
S No. | Theam changes | Time(In Hours)
4
4.1 | Theam layout changes on site. | 1 hour
| TOTAL | 1 hour
Till 30 March | Total time | 165 hour
From 1 April
S No. | EnergyLink changes | Time(In Hours) | Status
5
5.1 | When you select a main category, it should go to a sub-category page for business directory page | 14 | Done
we have done the page for business directory according to it's currently selected sub categeory, but on e categeory has 732 sub categeories which should affect the layout.
5.2 | My Link Navigation Bar – can we change the layout or size of buttons like the style we created (the original design). Don’t like 2 rows of buttons, needs to be one | 12 | Done
Work on progress
5.3 | New forget password page is created for reset password for site members. | 8 | Done
Task done, but some validation issue are remaining. There is two new pages were created for this task one for request reset password in the case of forget password, after request one mail is received on user's mail -id through he/she can reset their password.
5.4 | Profile progression bar is show only when current login user see own profile, if current user see the profile of another user profile progression bar not show.Also layout issues are solved for different browsers. | 5 | Done
This task is complete.
5.5 | Group Search is start according to Last active, Alphabatical, New Created, Most Members and also according to group's name. | 6 | Done
This task is complete.
5.6 | Feedback from working for site users. | 6 | Done
It is work properly, and it is open through lightbox.
5.7 | Contacts – we need to have a private or public check box so we don’t have to have all the contacts as public – not everyone wants their contacts to be seen | 14 | Done
This feature is not provide by Buddypress.it will take time
5.8 | Need to be able to include a small photo or avatar similar to Kijiji.com on main category page. | 12 | Done
This small photo is hendal by admin In backend
5.9 | Once registered, users should gain access to their profile immediately. Unless a user uses a different computer or mobile device, auto account access is important. | 14 | Done
Once I sign up, I should be able to access my profile immediately without entering my password on my landing page or header. This can be done in LinkedIn & Facebook. Do you understand? The registration pages do not work on IE 7 & 8, this critical that it works.
6 | Social Media Links (buttons) – where should we put them and then we need to decide which ones we need. | 6 | Done
6.1 | Pagination and searching should work proper on Energy Links. Searching must be done according to region and according to categeory. | 8 | Done
6.2 | we add 2 display adds for bussiness directory display profile page for 200 and 300 listing profile. | 6 | Done
6.3 | We done with the issue related to browser compatability. we replace images by text or button where it require & Also develop layout for some new pages. | 29 | Done
6.4 | my group search functionality done. | 4 | Done
6.5 | Site registration with mail activation complete | 8 | Done
6.6 | Display ads and Banner ads changing time interval is set by admin. | 6 | Done
6.7 | we done Featured employee image on job main page. | 12 | Done
this featured is handel by admin. Admin assign user featured or not. Featured employee image are showing on job main page
6.8 | set backend edit , delete, feature for all section in backend and layout as like admin | 28 | Done
admin handel the all listing which are showing on front end and action on it.
6.9 | Once someone adds Work Experience, Education, Additional Information, the button should change to “Update Work Experience”, etc, rather than “Add” | 8 | Done
7 | Once a user clicks a featured employer logo – it should go to their page that lists all the available positions or postings. Need to include the page layout for the featured employer. | 12 | Done
Depend on the PSD. And it will change the current system
7.1 | Need a group message or discussion reminder or transmission using email system (same as LinkedIn). Therefore, we need to ensure all users include their email address (mandatory field) | 14 | Done
ok Group update is send to members of group on mail.
7.2 | energy job: request for featured employer page. company featured profile page | 6 | Done
| Total time | 238
S No. | EnergyLink changes list | Time(Hr) | Status
3
3.1 | When clicking a link, it opens another page. Could we create an API so the site opens inside of EnergyLink website – is this possible? Could we do the same for Company Profile websites? |  | Upcoming Task | We are searching for that and we need api
Ok we need API for that. Please explain more about it
Total time

## Sheet2
1.1